## July.25
Progress Status | [14 empty] | Week 1 (01 Jul- 05 Jul) |  |  |  | 2025-07-01 |  | 2025-07-02 |  | 2025-07-03 |  | 2025-07-04 |  | 2025-07-05 |  | Week 2 (06 Jul - 12 Jul) |  |  |  | 2025-07-06 |  | 2025-07-07 |  | 2025-07-08 |  | 2025-07-09 |  | 2025-07-10 |  | 2025-07-11 |  | 2025-07-12 |  | Week 3 (13 Jul - 19 Jul) |  |  |  | 2025-07-13 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-07-16 |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-19 |  | Week 4 (20 Jul - 26 Jul) |  |  |  | 2025-07-20 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-07-24 |  | 2025-07-25 |  | 2025-07-26 |  | Week 5 (27 Jul - 30 Jul) |  |  |  | 2025-07-27 |  | 2025-07-28 |  | 2025-07-29 |  | 2025-07-30
Sr. No. | BOQ No. | Description | Location | Unit | BOQ/GFC Quantity | Completed Qty up to last month | Remaining Qty. | Planned Qty for this month | Rate | Planned Value | Start Date | End Date | Achieved Qty for the month | Achieved Amount | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty.
1 | 1 | Clearing and grubbing of top soil |  | Hectare | 20 | 38 | - | - | ₹ 46,547.25 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | 14 | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
2 | 2 | Excavation for foundation of all type of soil upto 1.5 mt depth |  | Cum. | 36790 | 14539 | 22250.69 | 219.15 | ₹ 117.93 | ₹ 25,843.26 | 2025-04-01 | 2025-04-30 | 52 | ₹ 6,132.10 | 36.53 | 4307 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 51.14 | 6030 | 52 | 6132 | 7.31 | - | 7.31 | - | 7.31 | 0 | 7.31 | - | 7.31 | 6 | 7.31 | - | 7.31 | - | 51.14 | 6030 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | 8 | 7.31 | - | 51.14 | 6030 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 29.22 | 3446 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | -
3 | 3 | Excavation for foundation of all type of soil 1.5 mt to 3.0 mt depth |  | Cum. | 7330 | 4769 | 2560.78 | - | ₹ 128.53 | ₹ - | 2025-04-01 | 2025-04-30 | 4 | ₹ 514.10 | - | 0 | - | 0 | - | - | 0 | - | - | - | - | - | - | - | - | 0 | 4 | 514 | - | - | - | - | - | 0 | - | 6 | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
4 | 4 | Excavation for foundation of all type of soil 3.0 to 5.0 mt depth |  | Cum. | 4330 | 2428 | 1901.8 | - | ₹ 140.45 | ₹ - | 2025-04-01 | 2025-04-30 | 23 | ₹ 3,230.35 | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | 23 | 3230 | - | - | - | - | - | 0 | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
5 | 5 | Extra (on item No.. 4) for excavation in additional depth more than 5.0 mt |  | Cum. | 240 | 444 | - | - | ₹ 18.55 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
6 | 6 | Embankment construction with selected approved materials from river |  | Cum. | 988820 | 325373 | 663446.87 | 110741.95 | ₹ 212.00 | ₹ 23,477,293.40 | 2025-04-01 | 2025-04-30 | 11760 | ₹ 2,493,120.00 | 18456.99 | 3912882 | 11760 | 2493120 | 3691.4 | 2389 | 3691.4 | 2089 | 3691.4 | 1075 | 3691.4 | 2914 | 3691.4 | 3293 | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 14765.59 | 3130306 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | -
7 | 8 | Embankment construction with selected approved good soil from any source outside the site area |  | Cum. | 1841740 | 1214758 | 626982.03 | 157200 | ₹ 299.45 | ₹ 47,073,540.00 | 2025-04-01 | 2025-04-30 | 39373.79 | ₹ 11,790,481.57 | 26200 | 7845590 | 39373.79 | 11790482 | 5240 | 10381 | 5240 | 9924 | 5240 | 8356 | 5240 | 2229 | 5240 | 8483.79 | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 20960 | 6276472 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | -
8 | 9 | Filling/ Backfilling with available selected/ approved excavated earth |  | Cum. | 48680 | 1659 | 47021.3 | - | ₹ 157.68 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
9 | 10 | Providing and laying in position Plain Cement Concrete (PCC) of M15 Grade |  | Cum. | 18220 | 2319 | 15900.85 | 393.88 | ₹ 4,303.60 | ₹ 1,695,099.39 | 2025-04-01 | 2025-04-30 | 101.04 | ₹ 434,835.74 | 19.69 | 84755 | 101.04 | 434836 | 3.94 | 1.5 | 3.94 | 7.29 | 3.94 | 48.28 | 3.94 | - | 3.94 | 43.97 | 55.14 | 237314 | - | 0 | 3.94 | - | 3.94 | - | 3.94 | - | 3.94 | - | 3.94 | - | 17.72 | - | 17.72 | - | 124.07 | 533956 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 124.07 | 533956 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 70.9 | 305118 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | -
10 | 11.1 | M25 - Concrete work for any vertical element such as Wall, Column, Stem, Key, steps etc. |  | Cum. | 22070 | 3018 | 19051.78 | 2126.85 | ₹ 7,869.18 | ₹ 16,736,576.62 | 2025-04-01 | 2025-04-30 | 51.64 | ₹ 406,356.33 | 106.34 | 836829 | 51.64 | 406356 | 21.27 | 4.19 | 21.27 | - | 21.27 | 18.24 | 21.27 | 12 | 21.27 | 17.21 | 297.76 | 2343121 | - | 0 | 21.27 | - | 21.27 | - | 21.27 | - | 21.27 | - | 21.27 | - | 95.71 | - | 95.71 | - | 669.96 | 5272022 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 669.96 | 5272022 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 382.83 | 3012584 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | -
11 | 11.2 | M25 - Concrete work for any foundation element such as Base, anchor slab etc. |  | Cum. | 44860 | 8394 | 36466.03 | 1132.2 | ₹ 5,837.95 | ₹ 6,609,720.54 | 2025-04-01 | 2025-04-30 | 87.18 | ₹ 508,952.48 | 56.61 | 330486 | 87.18 | 508952 | 11.32 | - | 11.32 | 76.18 | 11.32 | - | 11.32 | 11 | 11.32 | - | 158.51 | 925361 | - | 0 | 11.32 | - | 11.32 | - | 11.32 | - | 11.32 | - | 11.32 | - | 50.95 | - | 50.95 | - | 356.64 | 2082062 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 356.64 | 2082062 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 203.8 | 1189750 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | -
12 | 11.3 | M25 - Concrete work for any element such as top slab/ floor slab and beam for manhole, barrel, seating etc. |  | Cum. | 5150 | 2533 | 2616.69 | 416.03 | ₹ 7,851.95 | ₹ 3,266,609.19 | 2025-04-01 | 2025-04-30 | - | ₹ - | 20.8 | 163330 | - | 0 | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 58.24 | 457325 | - | 0 | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 18.72 | - | 18.72 | - | 131.05 | 1028982 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 131.05 | 1028982 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 74.88 | 587990 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | -
13 | 12.1 | M25 - Concrete work for any vertical element such as Wall, Column, Stem, Bench, Seating, coping etc. |  | Cum. | 48750 | 3672 | 45077.59 | 531.66 | ₹ 9,746.70 | ₹ 5,181,953.91 | 2025-04-01 | 2025-04-30 | - | ₹ - | 26.58 | 259098 | - | 0 | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 74.43 | 725474 | - | 0 | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 23.92 | - | 23.92 | - | 167.47 | 1632315 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 167.47 | 1632315 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 95.7 | 932752 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | -
14 | 12.2 | M25-Concrete work for element such as top slab/ floor slab |  | Cum. | 1900 | 0 | 1900 | 40 | ₹ 9,958.70 | ₹ 398,348.00 | 2025-04-01 | 2025-04-30 | - |  | 2 | 19917 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 5.6 | 55769 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 1.8 | - | 1.8 | - | 12.6 | 125480 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 12.6 | 125480 | - |  | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 7.2 | 71703 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | -
15 | 14 | Extra for Color Concrete |  | Cum. | 16370 | 0 | 16370 | 30.99 | ₹ 5,302.65 | ₹ 164,321.81 | 2025-04-01 | 2025-04-30 | - |  | 0.52 | 2739 | - | 0 | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 3.51 | 18623 | - | 0 | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 1.5 | - | 1.5 | - | 10.48 | 55596 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 10.48 | 55596 | - |  | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 5.99 | 31769 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | -
16 | 15 | Providing and fixing HYSD (TMT) Fe 500 D Reinforcement |  | Tonne | 8520 | 1201 | 7318.57 | 284.62 | ₹ 94,253.88 | ₹ 26,826,222.26 | 2025-04-01 | 2025-04-30 | 7.27 | ₹ 685,018.31 | 14.23 | 1341311 | 7.27 | 685018 | 2.85 | 0.35 | 2.85 | 3.75 | 2.85 | 1 | 2.85 | 1.15 | 2.85 | 1.02 | 39.85 | 3755671 | - | 0 | 2.85 | - | 2.85 | - | 2.85 | - | 2.85 | - | 2.85 | - | 12.81 | - | 12.81 | - | 89.65 | 8450260 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 89.65 | 8450260 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 51.23 | 4828720 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | -
17 | 16 | Providing and fixing premoulded compressible, high performance closed cell, bitumen free expansion joint filler board |  | sqmt | 3820 | 348 | 3472.03 | 51.33 | ₹ 1,040.13 | ₹ 53,388.59 | 2025-04-01 | 2025-04-30 | 0.69 | ₹ 717.69 | 8.55 | 8898 | 0.69 | 718 | 1.71 | - | 1.71 | 0.69 | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 6.84 | 7118 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | -
18 | 18 | Providing and filling the expansion joints for 25 mm width & 12 mm depth, with polysulphide sealant |  | Rmt | 19810 | 0 | 19810 | - | ₹ 381.60 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
19 | 19 | Providing and fixing 110 mm dia PVC pipe |  | Rmt | 7490 | 747 | 6742.9 | 95.39 | ₹ 519.40 | ₹ 49,546.09 | 2025-04-01 | 2025-04-30 | - | ₹ - | 15.9 | 8258 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 12.72 | 6606 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | -
20 | 20 | No. Fine concrete behind weep hole |  | Cum. | 8550 | 344 | 8205.99 | 65.61 | ₹ 4,832.28 | ₹ 317,045.56 | 2025-04-01 | 2025-04-30 | - | ₹ - | 3.28 | 15852 | - | 0 | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 9.19 | 44386 | - | 0 | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 2.95 | - | 2.95 | - | 20.67 | 99869 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 20.67 | 99869 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 11.81 | 57068 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | -
21 | 21 | Providing and fixing 120gsm No.n-woven type Geotextile |  | sqmt | 21050 | 47 | 21002.52 | 9.11 | ₹ 201.40 | ₹ 1,835.26 | 2025-04-01 | 2025-04-30 | - | ₹ - | 0.46 | 92 | - | 0 | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 1.28 | 257 | - | 0 | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.41 | - | 0.41 | - | 2.87 | 578 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 2.87 | 578 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 1.64 | 330 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | -
22 | 23 | Providing and laying Brick masonry works in manhole |  | Cum. | 2970 | 621 | 2349.45 | 272.07 | ₹ 6,155.95 | ₹ 1,674,868.52 | 2025-04-01 | 2025-04-30 | - | ₹ - | 13.6 | 83743 | - | 0 | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 38.09 | 234482 | - | 0 | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 12.24 | - | 12.24 | - | 85.7 | 527584 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 85.7 | 527584 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 48.97 | 301476 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | -
23 | 24 | Plastering work (12mm thick) |  | Sqmt | 13460 | 2333 | 11126.65 | 391.68 | ₹ 259.70 | ₹ 101,719.30 | 2025-04-01 | 2025-04-30 | - | ₹ - | 19.58 | 5086 | - | 0 | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 54.84 | 14241 | - | 0 | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 17.63 | - | 17.63 | - | 123.38 | 32042 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 123.38 | 32042 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 70.5 | 18309 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | -
24 | 28 | Providing and placing in position 225 mm wide x 12mm thick PVC water stops |  | Rmt | 8160 | 697 | 7463.11 | 69.7 | ₹ 681.05 | ₹ 47,471.02 | 2025-04-01 | 2025-04-30 | - | ₹ - | 11.62 | 7912 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 9.29 | 6329 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | -
25 | 43 | Rubble Soling works |  | Cum. | 200 | 0 | 200 | - | ₹ 996.40 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
26 | 44 | Structural Steel |  | KG | 163 | 0 | 370 | 1609.5 | ₹ 162.98 | ₹ 262,308.26 | 2025-04-01 | 2025-04-30 | 375 | ₹ 61,115.63 | 268.25 | 43718 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 61205 | 375 | 61116 | 53.65 | 6 | 53.65 | - | 53.65 | 25 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 61205 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | 170.6 | 53.65 | 108 | 53.65 | - | 375.55 | 61205 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 214.6 | 34974 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | -
27 | 45 | Hot Deep Galvanizing Work |  | KG | 70 | 0 | 370 | 1609.5 | ₹ 70.23 | ₹ 113,027.14 | 2025-04-01 | 2025-04-30 | 376 | ₹ 26,404.60 | 268.25 | 18838 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 26373 | 376 | 26405 | 53.65 | - | 53.65 | - | 53.65 | 26 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 26373 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | 30 | 53.65 | - | 375.55 | 26373 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 214.6 | 15070 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | -
28 | 48 | Coal tar extended epoxy resin on wall |  | Sqmt | 143960 | 9194 | 134766.4 | 1773.9 | ₹ 189.48 | ₹ 336,109.70 | 2025-04-01 | 2025-04-30 | 90 | ₹ 17,052.75 | 295.65 | 56018 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | 90 | 17053 | 59.13 | - | 59.13 | 40 | 59.13 | 50 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 236.52 | 44815 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | -
29 | 51 | Tree Pit Hume Pipe |  | Numbers | 2370 | 24 | 2346 | - | ₹ 3,747.00 | ₹ - | 2025-04-01 | 2025-04-30 | 12 | ₹ 44,964.00 | - | 0 | 12 | 44964 | - | - | - | - | - | 8 | - | - | - | 4 | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
30 | 56.2 | RCC NP3 Hume Pipe - 450mm dia. |  | Rmt | 9600 | 0 | 9600 | 40 | ₹ 2,147.83 | ₹ 85,913.00 | 2025-04-01 | 2025-04-30 | 23000 | ₹ 49,399,975.00 | 2 | 4296 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 5.6 | 12028 | 23000 | 49399975 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 1.8 | - | 1.8 | - | 12.6 | 27063 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 12.6 | 27063 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 7.2 | 15464 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | -
31 | 56.4 | RCC NP3 Hume Pipe - 900mm dia. |  | Rmt | 20 | 11 | 8.75 | 50 | ₹ 5,527.90 | ₹ 276,395.00 | 2025-04-01 | 2025-04-30 | 38000 | ₹ 210,060,200.00 | 2.5 | 13820 | - | 0 | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 7 | 38695 | 38000 | 210060200 | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 2.25 | - | 2.25 | - | 15.75 | 87064 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 15.75 | 87064 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 9 | 49751 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | -
32 | 57.1 | RCC NP4 Hume Pipe - 900mm dia. (Execution) |  | Rmt | 4270 | 1887 | 2383.2 | 500 | ₹ 2,334.65 | ₹ 1,167,325.00 | 2025-04-01 | 2025-04-30 | 17000 | ₹ 39,689,050.00 | 25 | 58366 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 70 | 163426 | 17000 | 39689050 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 22.5 | - | 22.5 | - | 157.5 | 367707 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 157.5 | 367707 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 90 | 210119 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | -
33 | 57.1.1 | RCC NP4 Hume Pipe - 900mm dia. (Supply) |  | Rmt | 4270 | 425 | 3845 | 300 | ₹ 6,070.09 | ₹ 1,821,027.00 | 2025-04-01 | 2025-04-30 | - | ₹ - | 15 | 91051 | - | 0 | 3 | - | 3 | - | 3 | - | 3 | - | 3 | - | 42 | 254944 | - | 0 | 3 | - | 3 | - | 3 | - | 3 | - | 3 | - | 13.5 | - | 13.5 | - | 94.5 | 573624 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 94.5 | 573624 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 54 | 327785 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | -
34 | 57.2 | RCC NP4 Hume Pipe - 1200mm dia. (Execution) |  | Rmt | 3100 | 3314 | - | 500 | ₹ 3,393.99 | ₹ 1,696,993.75 | 2025-04-01 | 2025-04-30 | - | ₹ - | 25 | 84850 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 70 | 237579 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 22.5 | - | 22.5 | - | 157.5 | 534553 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 157.5 | 534553 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 90 | 305459 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | -
35 | 57.2.1 | RCC NP4 Hume Pipe - 1200mm dia. (Supply) |  | Rmt | 3100 | 3885 | - | 150 | ₹ 8,824.37 | ₹ 1,323,655.13 | 2025-04-01 | 2025-04-30 | - | ₹ - | 7.5 | 66183 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 21 | 185312 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 6.75 | - | 6.75 | - | 47.25 | 416951 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 47.25 | 416951 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 27 | 238258 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | -
36 | 58 | Coat tar epoxy on on internal surface of RCC hume pipe |  | Sqmt | 40887.28 | 11053 | 29834.67 | 1884.96 | ₹ 189.48 | ₹ 357,151.96 | 2025-04-01 | 2025-04-30 | - | ₹ - | 314.16 | 59525 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 251.33 | 47620 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | -
37 | 59 | Providing and fixing FRP steps of size 500mmx150mmx25mm |  | Number | 4080 | 829 | 3251 | 140 | ₹ 651.90 | ₹ 91,266.00 | 2025-04-01 | 2025-04-30 | - | ₹ - | 23.33 | 15211 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 18.67 | 12169 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | -
38 | E-61 | 50mm diameter DWC Pipe |  | Cum. | 100 | 240 | - | 24 | ₹ 86.13 | ₹ 2,067.00 | 2025-04-01 | 2025-04-30 | 132 | ₹ 11,368.50 | 4 | 345 | 132 | 11369 | 0.8 | - | 0.8 | - | 0.8 | 75 | 0.8 | - | 0.8 | 57 | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 3.2 | 276 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | -
|  | TOTAL | [7 empty] | ₹ 141,234,642 |  |  |  | ₹ 315,639,489 |  | 15443306 |  | 16375815 | [11 empty] | 26478109 |  | 299263675 | [15 empty] | 38621810 |  | 0 | [15 empty] | 38621810 |  | 0 | [15 empty] | 22069606 |  | 0

## Sheet2
Progress Status | [14 empty] | Week 1 (01 Jul- 05 Jul) |  |  |  | 2025-07-01 |  | 2025-07-02 |  | 2025-07-03 |  | 2025-07-04 |  | 2025-07-05 |  | Week 2 (06 Jul - 12 Jul) |  |  |  | 2025-07-06 |  | 2025-07-07 |  | 2025-07-08 |  | 2025-07-09 |  | 2025-07-10 |  | 2025-07-11 |  | 2025-07-12 |  | Week 3 (13 Jul - 19 Jul) |  |  |  | 2025-07-13 |  | 2025-07-14 |  | 2025-07-15 |  | 2025-07-16 |  | 2025-07-17 |  | 2025-07-18 |  | 2025-07-19 |  | Week 4 (20 Jul - 26 Jul) |  |  |  | 2025-07-20 |  | 2025-07-21 |  | 2025-07-22 |  | 2025-07-23 |  | 2025-07-24 |  | 2025-07-25 |  | 2025-07-26 |  | Week 5 (27 Jul - 30 Jul) |  |  |  | 2025-07-27 |  | 2025-07-28 |  | 2025-07-29 |  | 2025-07-30
Sr. No. | BOQ No. | Description | Location | Unit | BOQ/GFC Quantity | Completed Qty up to last month | Remaining Qty. | Planned Qty for this month | Rate | Planned Value | Start Date | End Date | Achieved Qty for the month | Achieved Amount | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Amount | Achieved Qty. | Amount | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty. | Planned Qty. | Achieved Qty.
1 | 1 | Clearing and grubbing of top soil |  | Hectare | 20 | 38 | - | - | ₹ 46,547.25 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | 14 | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
2 | 2 | Excavation for foundation of all type of soil upto 1.5 mt depth |  | Cum. | 36790 | 14539 | 22250.69 | 219.15 | ₹ 117.93 | ₹ 25,843.26 | 2025-04-01 | 2025-04-30 | 52 | ₹ 6,132.10 | 36.53 | 4307 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 51.14 | 6030 | 52 | 6132 | 7.31 | - | 7.31 | - | 7.31 | 0 | 7.31 | - | 7.31 | 6 | 7.31 | - | 7.31 | - | 51.14 | 6030 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 51.14 | 6030 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | - | 29.22 | 3446 | - | 0 | 7.31 | - | 7.31 | - | 7.31 | - | 7.31 | -
3 | 3 | Excavation for foundation of all type of soil 1.5 mt to 3.0 mt depth |  | Cum. | 7330 | 4769 | 2560.78 | - | ₹ 128.53 | ₹ - | 2025-04-01 | 2025-04-30 | 4 | ₹ 514.10 | - | 0 | - | 0 | - | - | 0 | - | - | - | - | - | - | - | - | 0 | 4 | 514 | - | - | - | - | - | 0 | - | 6 | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
4 | 4 | Excavation for foundation of all type of soil 3.0 to 5.0 mt depth |  | Cum. | 4330 | 2428 | 1901.8 | - | ₹ 140.45 | ₹ - | 2025-04-01 | 2025-04-30 | 23 | ₹ 3,230.35 | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | 23 | 3230 | - | - | - | - | - | 0 | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
5 | 5 | Extra (on item No.. 4) for excavation in additional depth more than 5.0 mt |  | Cum. | 240 | 444 | - | - | ₹ 18.55 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
6 | 6 | Embankment construction with selected approved materials from river |  | Cum. | 988820 | 325373 | 663446.87 | 110741.95 | ₹ 212.00 | ₹ 23,477,293.40 | 2025-04-01 | 2025-04-30 | 11760 | ₹ 2,493,120.00 | 18456.99 | 3912882 | 11760 | 2493120 | 3691.4 | 2389 | 3691.4 | 2089 | 3691.4 | 1075 | 3691.4 | 2914 | 3691.4 | 3293 | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 25839.79 | 5478035 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | - | 14765.59 | 3130306 | - | 0 | 3691.4 | - | 3691.4 | - | 3691.4 | - | 3691.4 | -
7 | 8 | Embankment construction with selected approved good soil from any source outside the site area |  | Cum. | 1841740 | 1214758 | 626982.03 | 157200 | ₹ 299.45 | ₹ 47,073,540.00 | 2025-04-01 | 2025-04-30 | 39373.79 | ₹ 11,790,481.57 | 26200 | 7845590 | 39373.79 | 11790482 | 5240 | 10381 | 5240 | 9924 | 5240 | 8356 | 5240 | 2229 | 5240 | 8483.79 | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 36680 | 10983826 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 5240 | - | 20960 | 6276472 | - | 0 | 5240 | - | 5240 | - | 5240 | - | 5240 | -
8 | 9 | Filling/ Backfilling with available selected/ approved excavated earth |  | Cum. | 48680 | 1659 | 47021.3 | - | ₹ 157.68 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
9 | 10 | Providing and laying in position Plain Cement Concrete (PCC) of M15 Grade |  | Cum. | 18220 | 2319 | 15900.85 | 393.88 | ₹ 4,303.60 | ₹ 1,695,099.39 | 2025-04-01 | 2025-04-30 | 101.04 | ₹ 434,835.74 | 19.69 | 84755 | 101.04 | 434836 | 3.94 | 1.5 | 3.94 | 7.29 | 3.94 | 48.28 | 3.94 | - | 3.94 | 43.97 | 55.14 | 237314 | - | 0 | 3.94 | - | 3.94 | - | 3.94 | - | 3.94 | - | 3.94 | - | 17.72 | - | 17.72 | - | 124.07 | 533956 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 124.07 | 533956 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | - | 70.9 | 305118 | - | 0 | 17.72 | - | 17.72 | - | 17.72 | - | 17.72 | -
10 | 11.1 | M25 - Concrete work for any vertical element such as Wall, Column, Stem, Key, steps etc. |  | Cum. | 22070 | 3018 | 19051.78 | 2126.85 | ₹ 7,869.18 | ₹ 16,736,576.62 | 2025-04-01 | 2025-04-30 | 51.64 | ₹ 406,356.33 | 106.34 | 836829 | 51.64 | 406356 | 21.27 | 4.19 | 21.27 | - | 21.27 | 18.24 | 21.27 | 12 | 21.27 | 17.21 | 297.76 | 2343121 | - | 0 | 21.27 | - | 21.27 | - | 21.27 | - | 21.27 | - | 21.27 | - | 95.71 | - | 95.71 | - | 669.96 | 5272022 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 669.96 | 5272022 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | - | 382.83 | 3012584 | - | 0 | 95.71 | - | 95.71 | - | 95.71 | - | 95.71 | -
11 | 11.2 | M25 - Concrete work for any foundation element such as Base, anchor slab etc. |  | Cum. | 44860 | 8394 | 36466.03 | 1132.2 | ₹ 5,837.95 | ₹ 6,609,720.54 | 2025-04-01 | 2025-04-30 | 87.18 | ₹ 508,952.48 | 56.61 | 330486 | 87.18 | 508952 | 11.32 | - | 11.32 | 76.18 | 11.32 | - | 11.32 | 11 | 11.32 | - | 158.51 | 925361 | - | 0 | 11.32 | - | 11.32 | - | 11.32 | - | 11.32 | - | 11.32 | - | 50.95 | - | 50.95 | - | 356.64 | 2082062 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 356.64 | 2082062 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | - | 203.8 | 1189750 | - | 0 | 50.95 | - | 50.95 | - | 50.95 | - | 50.95 | -
12 | 11.3 | M25 - Concrete work for any element such as top slab/ floor slab and beam for manhole, barrel, seating etc. |  | Cum. | 5150 | 2533 | 2616.69 | 416.03 | ₹ 7,851.95 | ₹ 3,266,609.19 | 2025-04-01 | 2025-04-30 | - | ₹ - | 20.8 | 163330 | - | 0 | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 58.24 | 457325 | - | 0 | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 4.16 | - | 18.72 | - | 18.72 | - | 131.05 | 1028982 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 131.05 | 1028982 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | - | 74.88 | 587990 | - | 0 | 18.72 | - | 18.72 | - | 18.72 | - | 18.72 | -
13 | 12.1 | M25 - Concrete work for any vertical element such as Wall, Column, Stem, Bench, Seating, coping etc. |  | Cum. | 48750 | 3672 | 45077.59 | 531.66 | ₹ 9,746.70 | ₹ 5,181,953.91 | 2025-04-01 | 2025-04-30 | - | ₹ - | 26.58 | 259098 | - | 0 | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 74.43 | 725474 | - | 0 | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 5.32 | - | 23.92 | - | 23.92 | - | 167.47 | 1632315 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 167.47 | 1632315 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | - | 95.7 | 932752 | - | 0 | 23.92 | - | 23.92 | - | 23.92 | - | 23.92 | -
14 | 12.2 | M25-Concrete work for element such as top slab/ floor slab |  | Cum. | 1900 | 0 | 1900 | 40 | ₹ 9,958.70 | ₹ 398,348.00 | 2025-04-01 | 2025-04-30 | - |  | 2 | 19917 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 5.6 | 55769 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 1.8 | - | 1.8 | - | 12.6 | 125480 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 12.6 | 125480 | - |  | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 7.2 | 71703 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | -
15 | 14 | Extra for Color Concrete |  | Cum. | 16370 | 0 | 16370 | 30.99 | ₹ 5,302.65 | ₹ 164,321.81 | 2025-04-01 | 2025-04-30 | - |  | 0.52 | 2739 | - | 0 | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 3.51 | 18623 | - | 0 | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 0.1 | - | 1.5 | - | 1.5 | - | 10.48 | 55596 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 10.48 | 55596 | - |  | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 5.99 | 31769 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | -
16 | 15 | Providing and fixing HYSD (TMT) Fe 500 D Reinforcement |  | Tonne | 8520 | 1201 | 7318.57 | 284.62 | ₹ 94,253.88 | ₹ 26,826,222.26 | 2025-04-01 | 2025-04-30 | 7.27 | ₹ 685,018.31 | 14.23 | 1341311 | 7.27 | 685018 | 2.85 | 0.35 | 2.85 | 3.75 | 2.85 | 1 | 2.85 | 1.15 | 2.85 | 1.02 | 39.85 | 3755671 | - | 0 | 2.85 | - | 2.85 | - | 2.85 | - | 2.85 | - | 2.85 | - | 12.81 | - | 12.81 | - | 89.65 | 8450260 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 89.65 | 8450260 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | - | 51.23 | 4828720 | - | 0 | 12.81 | - | 12.81 | - | 12.81 | - | 12.81 | -
17 | 16 | Providing and fixing premoulded compressible, high performance closed cell, bitumen free expansion joint filler board |  | sqmt | 3820 | 348 | 3472.03 | 51.33 | ₹ 1,040.13 | ₹ 53,388.59 | 2025-04-01 | 2025-04-30 | 0.69 | ₹ 717.69 | 8.55 | 8898 | 0.69 | 718 | 1.71 | - | 1.71 | 0.69 | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 11.98 | 12457 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | - | 6.84 | 7118 | - | 0 | 1.71 | - | 1.71 | - | 1.71 | - | 1.71 | -
18 | 18 | Providing and filling the expansion joints for 25 mm width & 12 mm depth, with polysulphide sealant |  | Rmt | 19810 | 0 | 19810 | - | ₹ 381.60 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
19 | 19 | Providing and fixing 110 mm dia PVC pipe |  | Rmt | 7490 | 747 | 6742.9 | 95.39 | ₹ 519.40 | ₹ 49,546.09 | 2025-04-01 | 2025-04-30 | - | ₹ - | 15.9 | 8258 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 22.26 | 11561 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | - | 12.72 | 6606 | - | 0 | 3.18 | - | 3.18 | - | 3.18 | - | 3.18 | -
20 | 20 | No. Fine concrete behind weep hole |  | Cum. | 8550 | 344 | 8205.99 | 65.61 | ₹ 4,832.28 | ₹ 317,045.56 | 2025-04-01 | 2025-04-30 | - | ₹ - | 3.28 | 15852 | - | 0 | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 9.19 | 44386 | - | 0 | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 0.66 | - | 2.95 | - | 2.95 | - | 20.67 | 99869 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 20.67 | 99869 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | - | 11.81 | 57068 | - | 0 | 2.95 | - | 2.95 | - | 2.95 | - | 2.95 | -
21 | 21 | Providing and fixing 120gsm No.n-woven type Geotextile |  | sqmt | 21050 | 47 | 21002.52 | 9.11 | ₹ 201.40 | ₹ 1,835.26 | 2025-04-01 | 2025-04-30 | - | ₹ - | 0.46 | 92 | - | 0 | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 1.28 | 257 | - | 0 | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.09 | - | 0.41 | - | 0.41 | - | 2.87 | 578 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 2.87 | 578 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | - | 1.64 | 330 | - | 0 | 0.41 | - | 0.41 | - | 0.41 | - | 0.41 | -
22 | 23 | Providing and laying Brick masonry works in manhole |  | Cum. | 2970 | 621 | 2349.45 | 272.07 | ₹ 6,155.95 | ₹ 1,674,868.52 | 2025-04-01 | 2025-04-30 | - | ₹ - | 13.6 | 83743 | - | 0 | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 38.09 | 234482 | - | 0 | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 2.72 | - | 12.24 | - | 12.24 | - | 85.7 | 527584 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 85.7 | 527584 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | - | 48.97 | 301476 | - | 0 | 12.24 | - | 12.24 | - | 12.24 | - | 12.24 | -
23 | 24 | Plastering work (12mm thick) |  | Sqmt | 13460 | 2333 | 11126.65 | 391.68 | ₹ 259.70 | ₹ 101,719.30 | 2025-04-01 | 2025-04-30 | - | ₹ - | 19.58 | 5086 | - | 0 | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 54.84 | 14241 | - | 0 | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 3.92 | - | 17.63 | - | 17.63 | - | 123.38 | 32042 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 123.38 | 32042 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | - | 70.5 | 18309 | - | 0 | 17.63 | - | 17.63 | - | 17.63 | - | 17.63 | -
24 | 28 | Providing and placing in position 225 mm wide x 12mm thick PVC water stops |  | Rmt | 8160 | 697 | 7463.11 | 69.7 | ₹ 681.05 | ₹ 47,471.02 | 2025-04-01 | 2025-04-30 | - | ₹ - | 11.62 | 7912 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 16.26 | 11077 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | - | 9.29 | 6329 | - | 0 | 2.32 | - | 2.32 | - | 2.32 | - | 2.32 | -
25 | 43 | Rubble Soling works |  | Cum. | 200 | 0 | 200 | - | ₹ 996.40 | ₹ - | 2025-04-01 | 2025-04-30 | - | ₹ - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
26 | 44 | Structural Steel |  | KG | 163 | 0 | 370 | 1609.5 | ₹ 162.98 | ₹ 262,308.26 | 2025-04-01 | 2025-04-30 | 375 | ₹ 61,115.63 | 268.25 | 43718 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 61205 | 375 | 61116 | 53.65 | 6 | 53.65 | - | 53.65 | 25 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 61205 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | 235.6 | 53.65 | - | 53.65 | - | 375.55 | 61205 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 214.6 | 34974 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | -
27 | 45 | Hot Deep Galvanizing Work |  | KG | 70 | 0 | 370 | 1609.5 | ₹ 70.23 | ₹ 113,027.14 | 2025-04-01 | 2025-04-30 | 376 | ₹ 26,404.60 | 268.25 | 18838 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 26373 | 376 | 26405 | 53.65 | - | 53.65 | - | 53.65 | 26 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 26373 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 375.55 | 26373 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | - | 214.6 | 15070 | - | 0 | 53.65 | - | 53.65 | - | 53.65 | - | 53.65 | -
28 | 48 | Coal tar extended epoxy resin on wall |  | Sqmt | 143960 | 9194 | 134766.4 | 1773.9 | ₹ 189.48 | ₹ 336,109.70 | 2025-04-01 | 2025-04-30 | 90 | ₹ 17,052.75 | 295.65 | 56018 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | 90 | 17053 | 59.13 | - | 59.13 | 40 | 59.13 | 50 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 413.91 | 78426 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | - | 236.52 | 44815 | - | 0 | 59.13 | - | 59.13 | - | 59.13 | - | 59.13 | -
29 | 51 | Tree Pit Hume Pipe |  | Numbers | 2370 | 24 | 2346 | - | ₹ 3,747.00 | ₹ - | 2025-04-01 | 2025-04-30 | 12 | ₹ 44,964.00 | - | 0 | 12 | 44964 | - | - | - | - | - | 8 | - | - | - | 4 | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 0 | - | 0 | - | - | - | - | - | - | - | -
30 | 56.2 | RCC NP3 Hume Pipe - 450mm dia. |  | Rmt | 9600 | 0 | 9600 | 40 | ₹ 2,147.83 | ₹ 85,913.00 | 2025-04-01 | 2025-04-30 | 23000 | ₹ 49,399,975.00 | 2 | 4296 | - | 0 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 5.6 | 12028 | 23000 | 49399975 | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 0.4 | - | 1.8 | - | 1.8 | - | 12.6 | 27063 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 12.6 | 27063 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | - | 7.2 | 15464 | - | 0 | 1.8 | - | 1.8 | - | 1.8 | - | 1.8 | -
31 | 56.4 | RCC NP3 Hume Pipe - 900mm dia. |  | Rmt | 20 | 11 | 8.75 | 50 | ₹ 5,527.90 | ₹ 276,395.00 | 2025-04-01 | 2025-04-30 | 38000 | ₹ 210,060,200.00 | 2.5 | 13820 | - | 0 | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 7 | 38695 | 38000 | 210060200 | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 0.5 | - | 2.25 | - | 2.25 | - | 15.75 | 87064 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 15.75 | 87064 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | - | 9 | 49751 | - | 0 | 2.25 | - | 2.25 | - | 2.25 | - | 2.25 | -
32 | 57.1 | RCC NP4 Hume Pipe - 900mm dia. (Execution) |  | Rmt | 4270 | 1887 | 2383.2 | 500 | ₹ 2,334.65 | ₹ 1,167,325.00 | 2025-04-01 | 2025-04-30 | 17000 | ₹ 39,689,050.00 | 25 | 58366 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 70 | 163426 | 17000 | 39689050 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 22.5 | - | 22.5 | - | 157.5 | 367707 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 157.5 | 367707 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 90 | 210119 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | -
33 | 57.1.1 | RCC NP4 Hume Pipe - 900mm dia. (Supply) |  | Rmt | 4270 | 425 | 3845 | 300 | ₹ 6,070.09 | ₹ 1,821,027.00 | 2025-04-01 | 2025-04-30 | - | ₹ - | 15 | 91051 | - | 0 | 3 | - | 3 | - | 3 | - | 3 | - | 3 | - | 42 | 254944 | - | 0 | 3 | - | 3 | - | 3 | - | 3 | - | 3 | - | 13.5 | - | 13.5 | - | 94.5 | 573624 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 94.5 | 573624 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | - | 54 | 327785 | - | 0 | 13.5 | - | 13.5 | - | 13.5 | - | 13.5 | -
34 | 57.2 | RCC NP4 Hume Pipe - 1200mm dia. (Execution) |  | Rmt | 3100 | 3314 | - | 500 | ₹ 3,393.99 | ₹ 1,696,993.75 | 2025-04-01 | 2025-04-30 | - | ₹ - | 25 | 84850 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 70 | 237579 | - | 0 | 5 | - | 5 | - | 5 | - | 5 | - | 5 | - | 22.5 | - | 22.5 | - | 157.5 | 534553 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 157.5 | 534553 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | - | 90 | 305459 | - | 0 | 22.5 | - | 22.5 | - | 22.5 | - | 22.5 | -
35 | 57.2.1 | RCC NP4 Hume Pipe - 1200mm dia. (Supply) |  | Rmt | 3100 | 3885 | - | 150 | ₹ 8,824.37 | ₹ 1,323,655.13 | 2025-04-01 | 2025-04-30 | - | ₹ - | 7.5 | 66183 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 21 | 185312 | - | 0 | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 1.5 | - | 6.75 | - | 6.75 | - | 47.25 | 416951 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 47.25 | 416951 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | - | 27 | 238258 | - | 0 | 6.75 | - | 6.75 | - | 6.75 | - | 6.75 | -
36 | 58 | Coat tar epoxy on on internal surface of RCC hume pipe |  | Sqmt | 40887.28 | 11053 | 29834.67 | 1884.96 | ₹ 189.48 | ₹ 357,151.96 | 2025-04-01 | 2025-04-30 | - | ₹ - | 314.16 | 59525 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 439.82 | 83335 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | - | 251.33 | 47620 | - | 0 | 62.83 | - | 62.83 | - | 62.83 | - | 62.83 | -
37 | 59 | Providing and fixing FRP steps of size 500mmx150mmx25mm |  | Number | 4080 | 829 | 3251 | 140 | ₹ 651.90 | ₹ 91,266.00 | 2025-04-01 | 2025-04-30 | - | ₹ - | 23.33 | 15211 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 32.67 | 21295 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | - | 18.67 | 12169 | - | 0 | 4.67 | - | 4.67 | - | 4.67 | - | 4.67 | -
38 | E-61 | 50mm diameter DWC Pipe |  | Cum. | 100 | 240 | - | 24 | ₹ 86.13 | ₹ 2,067.00 | 2025-04-01 | 2025-04-30 | 132 | ₹ 11,368.50 | 4 | 345 | 132 | 11369 | 0.8 | - | 0.8 | - | 0.8 | 75 | 0.8 | - | 0.8 | 57 | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 5.6 | 482 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | - | 3.2 | 276 | - | 0 | 0.8 | - | 0.8 | - | 0.8 | - | 0.8 | -
|  | TOTAL | [7 empty] | ₹ 141,234,642 |  |  |  | ₹ 315,639,489 |  | 15443306 |  | 16375815 | [11 empty] | 26478109 |  | 299263675 | [15 empty] | 38621810 |  | 0 | [15 empty] | 38621810 |  | 0 | [15 empty] | 22069606 |  | 0

## LOGS
Logged_At | Updated_Sheet | Name | Location | Description | Row | Column | Value
2025-07-17 23:48 | Sheet2 | test | val | 25 kg of structural string has been liberated. | 30 | 61 | 25
2025-07-17 23:57 | July.25 | test | val | 25 kg of structural string has been liberated. | 30 | 61 | 25
2025-07-18 00:17 | July.25 | test | dev | 10 kg Structural steel has been updated | 30 | 63 | 10
2025-07-18 00:17 | July.25 | test | dev | 10 kg Structural steel has been updated | 30 | 63 | 10
2025-07-18 00:18 | July.25 | test | dev | Twenty-five kg of structural steel has been updated. | 30 | 63 | 25
2025-07-18 00:19 | July.25 | test | dev | 30 kg of galerization has been done. | 31 | 63 | 30
2025-07-18 00:54 | July.25 | Test | Ashish | 25 kg of structural steel has been updated. | 30 | 63 | 25
2025-07-18 00:57 | July.25 | Test | Ashish | 10 kg of galvanized steel has been completed | 30 | 63 | 10
2025-07-18 00:57 | July.25 | Test | Ashish | 1 cubic meter of excavation of the 1.5 meter has been done | 6 | 63 | 1
2025-07-18 00:57 | July.25 | Raj | Rajkot | 7 cubic meter of excavation of the 1.5 meter is done | 6 | 63 | 7
2025-07-18 22:29 | July.25 | Mitesh | Ahmedbad | 10 cubic meter excavation and 25 kg structural steel works. | 30 | 63 | 25
2025-07-18 22:31 | July.25 | Mitesh | Ahmedbad | Three KG structural steel works happened on 18th July 2025. | 30 | 63 | 3